## Slide 1
Matt Scrivner / Assistant Road Master

## Slide 2: Full depth Reclamation Double chip seal

## Slide 3
Population 11,173
2,049 square miles
15,773 Registered Vehicles
State funding $863,654.00
County road system:
959 total centerline miles 358 miles Paved road
601 miles Gravel road
Road Crew:
Public Works Director
Management Assistant
Asst. Road Master
Working Foreman
(14) Maintenance Specialists
Mechanics
General maintenance
Snow removal
Sign repair and install
Bridge repair
Paint striping
Paving and Chip seals

## Slide 4
IONE-GOOSEBERRY Project 6.5 miles

## Slide 5: Asphalt overlay VS. Reclaim and Chip seal
Asphalt overlay of 6.5 miles of 24’ road
10,296 tons @ $62.50 (2015 pricing)
$643,500.00
Trucking would have been 1 ½ hours
One way from the plant. Estimated 575 tons per day. Would be 18 days of hauling to this project.
Same project at 2016 pricing would be
$ 548,262.00

## Slide 6: Reclaim with D6 and Roller

## Slide 7: Reclaimed Product
Large chunks that required multiple workings to get down to a size that was able to blade and compact for a drivable surface.

## Slide 8: RM 500

## Slide 9: Surface of road was 18’-20’ in width, patching had been done for many years. Severe alligator cracking on outer 4’ of both shoulders. An asphalt overlay would have been wasted dollars on this road.

## Slide 15: Very good product, 12” depth of reclaim on average

## Slide 16: Poor planning

## Slide 18: 1/2 mile rebuild of Peterson grade

## Slide 19: Grindings

## Slide 20: Compacted grindings

## Slide 21: Asphalt / Compacted grindings

## Slide 22: Timeline: May 2015 – Reclaim roadway *Bladed 3 times as standard gravel road June 6th-7th 2016 – Final grading / Compaction June 8th-9th 2016 - Soil Stabilization July 5th-19th 2016- Chip seal August 8th 2016 – Fog seal

## Slide 23: Earthbind applied at .40 shot rate (2nd coat shot rate of .10-.25)

## Slide 24: Wet on left / Cured on Right

## Slide 25: Cured / loose rock

## Slide 26: One month after Earthbind application

## Slide 32: First lift of chip seal ½” – ¾” rock & CRS 2PE oil at .60 shot rate

## Slide 36: 1ST LIFT

## Slide 39: Broom loose rock before 2nd lift

## Slide 40: 1st lift sweeping

## Slide 41: ¼” - 1/2” rock & CRS 2PE oil at .54 shot rate 2nd lift

## Slide 45: Sandi

## Slide 46: Final sweeping before fog seal

## Slide 49: Earthbind fog seal @ .12 shot rate

## Slide 50: Dirt pockets / Fog seal lifting

## Slide 51: Total oil cost for Project
Earthbind (Soil Stabalization)
.50 shot rate of solution $ 36,742.93
CRS 2PE (1st lift / ¾-1/2 rock)
.60 shot rate $ 100,098.60
CRS 2PE (2nd lift / ½-1/4 rock)
.54 shot rate $ 90,085.80
Earthbind (Fog seal)
.12 shot rate $ 12,868.20
Total project cost $ 239,795.53

## Slide 52: Cost comparison
Chart: 
2015 Asphalt costs | 643500
2016 Asphalt costs | 548262
2016 Double Chip seal | 239795.53

## Slide 53: Carlson lane / Ione-Gooseberry intersection
Before
After

## Slide 54: Peterson Grade
Before
After

## Slide 55: Dry-fork / Ione-Gooseberry intersection
Before
After

## Slide 56: Questions
Matt Scrivner
Assistant Road Master
Morrow County Public Works
mscrivner@co.morrow.or.us
541-989-8584
Burke O’Brien
Public Works Director
Morrow County Public Works
bobrien@co.morrow.or.us
541-989-8317
Troy Tindall
Blue Line Transportation
troy@bluelinetrans.com
503-702-1236