## Slide 1: CHIP SEAL EFFICIENCY IN OPERATIONS
MORROW COUNTY
2018-2019
Eric Imes
541-256-0576

## Slide 2: INTRODUCTION
Chip Seal Operations Planning
Pre Construction Meeting
Post Construction Meeting
Data Entry

## Slide 3: CHIP SEAL OPERATIONS PLANNING
Crew and Equipment Capabilities
Rock source
Equipment Staging
Municipality Communication
Land Owner Communication
Asphalt Supplier Capabilities
Projected Schedule
Back Up Plan

## Slide 5
CHIP SEAL FISCAL YEAR 2018 |  |  |  |  |  |  |  |  | 
ROAD NAME | projected date | AREA | MILES | LENGTH | WIDTH | SQUARE YDS. | projected rock tons | projected gallons | projected shot
ALPINE | june 3rd. | North Lexington | 2.12 | 11200 | 20 | 24889 | 261 | 11200 | 0.45
PATTERSON FERRY north of 730 | june 4th. | Irrigon | 3.34 | 17635 | 26 | 50946 | 535 | 21907 | 0.43
PATTERSON FERRY south of 730 | june 5th. | Irrigon | 2.86 | 15101 | 26 | 43625 | 458 | 18759 | 0.43
COLUMBIA | june 5,6 | Irrigon | 2.43 | 12830 | 25 | 35639 | 374 | 17820 | 0.5
KUNZE west of main | june 6,10 | Boardman | 4.78 | 25239 | 33.5 | 93945 | 986 | 39457 | 0.42
KUNZE east of main | june 11th. | Boardman | 1.24 | 6547 | 22-24 | 16731 | 176 | 7362 | 0.44
MILLER | june 11th. | Boardman | 0.5 | 2660 | 20 | 5911 | 89 | 2956 | 0.5
PETERS north of Kunze | june 11th. | Boardman | 0.5 | 2630 | 20 | 5844 | 61 | 2630 | 0.45
TOMS CAMP north of Kunze | june 11th. | Boardman | 0.5 | 2650 | 20 | 5889 | 88 | 2945 | 0.5
WILSON west of Paul Smith | june 12th. | Boardman | 2.39 | 12640 | 29 | 40729 | 428 | 18328 | 0.45
TOWER | june 13,17,18 | Boardman | 8.3 | 43845 | 26 | 126663 | 1330 | 53199 | 0.42
TOTAL |  |  | 28.96 | 152977 |  | 450811 | 4786 | 196563 | 0.454

## Slide 6: PRE CONSTRUCTION MEETING
Oil award
  RFQ
  Project cost comparison
  Expectations of oil supplier
Flagging
  Lead men leave shop @ 6:00
  Manage sign sets
  Briefing w/ hired flaggers on days schedule & JHA
  Communicate with hired flaggers/sign time slips
  Shadow brooms when necessary
Brooms
  Sweep ahead of chip crew
  Pull stick n’ stomps
  Sweep chip seal
Distributer
  Has right of way
    Limited sight distance
    Many distractions
  Extreme danger while shooting intersections and turn lanes
  Hot oil under pressure
    Maintain 20 feet of space between you and back end of truck
  Expect sudden changes in movements/direction
Chip spreader
  Stay aboard unless communicated with operator
  Expect sudden changes in movements/direction
  Operator will hook to trucks
  Watch belt man for hand signals
Haul trucks
  Communicate with lead driver on protocol
    Route
    Loading procedures
    Entering construction zone
    In construction zone staging
    Leaving chip spreader
  Communicate with belt man by hand signals
  Try to cross meet lines where others have also
  Spit tracks
  Look for chip rock problems on road
  Keep track of loads per road

## Slide 8: PRE CONSTRUCTION MEETING
Rollers
  Patterns
    Watch for well rolled wheel paths
  Sections
    Roll in sections to make room for ground crew
  Safety
    Three point contact rule
    Look before changing directions
    Watch for ground crew
    Shoulders
Ground crew
  Repair imperfections
  Rake joints
  Sweep & rake intersections
  Stick n’ stomps
  Safety
    Constant personal awareness
    Always have an escape route
Chip Seal Foreman
  Quality control
    Roadway prep
    Communicate with oil supplier on oil and rock rates
    Communicate with lead men
  Organize stock pile sites
    Floor prep
    Rock quantities
    Loader logistics
  Staging sites for equipment and oil tankers
    Communicate with landowners
    Prep stage location
  Manage schedule
    Project dates and locations
    Communicate with municipalities and schools
    Communicate with land owners (harvest)
    Manage operational changes

## Slide 10: POST CONSTRUCTION MEETING
Discussed what went well
Discussed what to change
Discussed safety concerns
It was valuable discussion

## Slide 11: DATA ENTRY
CHIP SEAL FISCAL YEAR 2018 |  |  |  |  |  |  |  |  |  |  |  | 
ROAD NAME | projected date | actual date | AREA | MILES | LENGTH | WIDTH | SQUARE YDS. | projected gallons | projected shot | square yds shot | gallons shot | shot rate
ALPINE | june 3rd. | june 3rd | North Lexington | 2.12 | 11200 | 20 | 24889 | 11200 | 0.45 | 26874 | 11100 | 0.413
PATTERSON FERRY north of 730 | june 4th. | june 4th | Irrigon | 3.34 | 17635 | 26 | 50946 | 21907 | 0.43 | 52380 | 22725 | 0.434
PATTERSON FERRY south of 730 | june 5th. | june 5,6 | Irrigon | 2.86 | 15101 | 26 | 43625 | 18759 | 0.43 | 42723 | 19725 | 0.462
COLUMBIA | june 5,6 | june 4,5 | Irrigon | 2.43 | 12830 | 25 | 35639 | 17820 | 0.5 | 37133 | 16600 | 0.447
KUNZE west of main | june 6,10 | june 6,10 | Boardman | 4.78 | 25239 | 33.5 | 93945 | 39457 | 0.42 | 93673 | 45244 | 0.483
KUNZE east of main | june 11th. | june 11th. | Boardman | 1.24 | 6547 | 22-24 | 16731 | 7362 | 0.44 | 16731 | 8081 | 0.483
MILLER | june 11th. | june 11th. | Boardman | 0.5 | 2660 | 20 | 5911 | 2956 | 0.5 | 6879 | 3725 | 0.542
PETERS north of Kunze | june 11th. | june 10th. | Boardman | 0.5 | 2630 | 20 | 5844 | 2630 | 0.45 | 6456 | 3050 | 0.472
TOMS CAMP north of Kunze | june 11th. | june 11th. | Boardman | 0.5 | 2650 | 20 | 5889 | 2945 | 0.5 | 6333 | 3500 | 0.553
WILSON west of Paul Smith | june 12th. | june 12th. | Boardman | 2.39 | 12640 | 29 | 40729 | 18328 | 0.45 | 41395 | 19400 | 0.469
TOWER | june 13,17,18 | june 12,13,17 | Boardman | 8.3 | 43845 | 26 | 126663 | 53199 | 0.42 | 127233 | 57250 | 0.45
TOTAL |  |  |  | 28.96 | 152977 |  | 450811 | 196563 | 0.454 | 457810 | 210400 | 0.46
FOG SEAL FISCAL YEAR 2018 |  |  |  |  |  |  |  |  |  |  |  | 
ROAD NAME | projected date | actual date | AREA | MILES | LENGTH | WIDTH | SQUARE YDS. | projected gallons | projected shot | square yds shot | gallons shot | shot rate
ALPINE |  |  | North Lexington |  |  |  |  |  |  |  |  | 
PATTERSON FERRY north of 207 | june 19th. | june 18th. | Irrigon | 3.34 | 17635 | 26 | 50946 | 6114 | 0.12 | 51931 | 5193 | 0.1
PATTERSON FERRY south of 207 | june 19,20 | june 18th. | Irrigon | 2.86 | 15101 | 26 | 43625 | 5235 | 0.12 | 44590 | 4459 | 0.1
COLUMBIA | june 20th. | june 18th. | Irrigon | 2.43 | 12830 | 25 | 35639 | 4277 | 0.12 | 37619 | 4425 | 0.118
KUNZE west of main | june 20,24 | june 19th. | Boardman | 4.78 | 25239 | 33.5 | 93945 | 11273 | 0.12 | 94522 | 9830 | 0.104
KUNZE east of main | june 24th. | june 19th. | Boardman | 1.24 | 6547 | 22-24 | 16731 | 2008 | 0.12 | 17464 | 1816 | 0.104
MILLER | june 25th. | june 19th. | Boardman | 0.5 | 2660 | 20 | 5911 | 709 | 0.12 | 6695 | 675 | 0.101
PETERS north of Kunze | june 25th. | june 19th. | Boardman | 0.5 | 2630 | 20 | 5844 | 701 | 0.12 | 6695 | 675 | 0.101
TOM CAMP | june 25th. | june 19th. | Boardman | 0.5 | 2650 | 20 | 5889 | 707 | 0.12 | 6695 | 675 | 0.101
WILSON west of Paul Smith | june 26th. | june 19th. | Boardman | 2.39 | 12640 | 29 | 40729 | 4888 | 0.12 | 42476 | 4375 | 0.103
TOWER | june 26th. | june 20th. | Boardman | 8.3 | 43845 | 26 | 126663 | 15200 | 0.12 | 127117 | 13200 | 0.104
TOTAL | 15 days | 12 days |  | 26.84 | 141777 |  | 425922 | 51112 | 0.12 | 435804 | 45323 | 0.1036

## Slide 12: DATA ENTRY
CHIP SEAL FISCAL YEAR 2019 |  |  |  |  |  |  |  |  |  |  |  | 
ROAD NAME | projected date | actual date | AREA | MILES | LENGTH | WIDTH | SQUARE YDS. | projected gallons | projected shot | square yds shot | gallons shot | shot rate
RHEA CREEK BRIDGE SECTION | 19-Aug | 19-Aug | IONE | 0.587 | 3100 | 24 | 8267 | 3968 | 0.48 | 8194 | 4000 | 0.488
IONE-GOOSEBERRY | 20-Aug | 20-Aug | IONE | 19.54 | 103152 | 22-31 | 276900 | 132912 | 0.48 | 281183 | 135550 | 0.482
 | 21-Aug | 21-Aug |  |  |  |  |  |  |  |  |  | 
 | 22-Aug | 22-Aug |  |  |  |  |  |  |  |  |  | 
 | 26-Aug | 26-Aug |  |  |  |  |  |  |  |  |  | 
 | 27-Aug | 27-Aug |  |  |  |  |  |  |  |  |  | 
 | 28-Aug |  |  |  |  |  |  |  |  |  |  | 
private aircraft |  |  |  |  |  |  |  |  |  |  |  | 
hanger apron and taxiway |  |  |  |  |  |  |  |  |  |  |  | 
were added and completed |  |  |  |  |  |  |  |  |  |  |  | 
in this time frame |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 20.127 | 106252 |  | 285167 | 136880 | 0.480 | 289377 | 139550 | 0.485
FOG SEAL FISCAL YEAR 2019 |  |  |  |  |  |  |  |  |  |  |  | 
ROAD NAME | projected date | actual date | AREA | MILES | LENGTH | WIDTH | SQUARE YDS. | projected gallons | projected shot | square yds shot | gallons shot | shot rate
RHEA CREEK BRIDGE SECTION | 29-Aug | 28-Aug | IONE | 0.587 | 3100 | 24 | 8267 | 992 | 0.12 | 8327 | 1100 | 0.13
IONE-GOOSEBERRY | 3-Sep | 28-Aug | IONE | 19.54 | 103152 | 22-31 | 276900 | 27690 | 0.1 | 293267 | 40925 | 0.14
 | 4-Sep | 29-Aug |  |  |  |  |  |  |  |  |  | 
 | 5-Sep |  |  |  |  |  |  |  |  |  |  | 
private aircraft |  |  |  |  |  |  |  |  |  |  |  | 
hanger apron and taxiway |  |  |  |  |  |  |  |  |  |  |  | 
were added and completed |  |  |  |  |  |  |  |  |  |  |  | 
in this time frame |  |  |  |  |  |  |  |  |  |  |  | 
 | 11 days | 8 days |  | 20.127 | 106252 |  | 285167 | 28682 | 0.11 | 301594 | 42025 | 0.135

## Slide 15: IN CLOSING
Faster Capabilities = more oil on the ground in a day
Faster pump turnaround = more oil on the ground in a day
Seamless Flagging = more oil on the ground in a day
Matching rock trucks to dist = more oil on the ground in a day
Maximum oil on the ground in a day = maximum project efficiency
7 DAYS AHEAD OF SCHEDULE & LOWER ROCK RATES SAVED AN ADDITIONAL $204,000 IN TOTAL PROJECT COSTS THIS YEAR
Eric Imes 541-256-0576